## Implementation
Project | Root Work Package | Version | Epic | Parent | Story ID | Subject | Goal | Acceptance Criteria | Non-Goals | Implementation Notes | Requirement IDs | Predecessors | Type | Status | Branch Name | OpenProject ID | Notes
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-001 | Define the validated report domain model | Provide a typed, renderer-neutral model that represents report metadata, ordered content, findings, artifacts, publication tables, and semantic finding metadata. | The model represents report metadata, ordered sections, findings, narrative text, chart references, tables, appendices, and renderer hints. Publication tables represent column identity, labels, row data, formats, alignment, captions, notes, and renderer hints without analytical computation. Validation rejects missing required structure and missing referenced local artifacts before rendering begins. Validation errors identify the failing report element and artifact. Public model interfaces are type annotated and covered by automated tests. | Rendering, analytical computation, SQL execution, chart construction, and report prose authoring are outside this story. | Inspect the initialized repository before choosing modules or file paths. Implement the smallest typed domain model that satisfies the mapped requirements and verify deterministic ordering in unit tests. | FR-001, FR-008, FR-022, FR-031, QR-003, QR-005 |  | Story | New | wr-001-define-the-validated-report-domain-model | 360 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-002 | Compile declarative report sources | Compile YAML report definitions and Markdown findings with frontmatter and bounded Jinja substitution into the validated report domain model. | YAML defines report composition, section order, finding references, artifact references, and renderer metadata. Markdown findings support YAML frontmatter and optional Jinja value substitution and presentation formatting. Compilation produces the same typed domain model available to programmatic consumers. Templates cannot perform metric computation, analytical interpretation, business-outcome branching, or structural control. Invalid authoring input returns an error that identifies the source and field. | Renderer implementation and analytical metric computation are outside this story. | Use schema-driven parsing and tests covering valid compilation, invalid input, and prohibited template behavior. Exact repository placement requires inspection. | FR-011, FR-012, FR-013, FR-014 | WR-001 | Story | New | wr-002-compile-declarative-report-sources | 361 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-003 | Resolve logical charts through the generation pipeline | Resolve stable logical chart identifiers to consuming-project chart builders and generate chart artifacts after report semantics are compiled. | Report definitions reference charts by stable logical identifiers rather than module paths or function names. A consuming repository can supply a mapping from logical identifiers to project-specific chart builders. The generation workflow passes resolved title, subtitle, source, run context, and visual references consistently to chart generation and document renderers. Externally produced chart artifacts, including wood-charts exports, are accepted without reimplementing chart rendering. A missing logical chart identifier produces an explicit validation error. | Wood Reports does not own project-specific chart construction, chart themes, or analytical queries. | Define the integration contract without naming project files until the repository and consuming example are inspected. Cover registry resolution and missing-artifact behavior with tests. | FR-006, FR-034, FR-035, FR-036 | WR-001, WR-002 | Story | New | wr-003-resolve-logical-charts-through-the-generation-pipeline | 362 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-004 | Render PowerPoint report layouts | Render report specifications into valid PowerPoint presentations with reusable layouts and editable report-level text. | A valid PowerPoint file is generated from the shared report model. Title, section, finding-with-chart, finding-with-table, and summary layouts are supported. Finding title, subtitle, source, and dynamic page number are native editable presentation text on chart slides. Chart-content exports omit report-level title, subtitle, and source, while full-frame chart exports remain supported. Renderer-specific hints can change presentation layout without requiring a separate report definition. PowerPoint output can be generated independently or with another renderer. | Chart construction, chart styling, and pixel-identical parity with LaTeX are outside this story. | Select the PowerPoint library after repository inspection and a small layout-fidelity spike. Add automated package-open validation and fixture-based layout assertions. | FR-002, FR-004, FR-007, FR-010, FR-032, FR-033 | WR-003 | Story | New | wr-004-render-powerpoint-report-layouts | 363 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-005 | Render publication tables in PowerPoint | Render shared publication tables into presentation-appropriate PowerPoint layouts without changing their analytical meaning. | Shared table data renders as native PowerPoint table content. Typography, sizing, emphasis, row limits, and placement follow explicit presentation hints. Presentation hints do not mutate source rows, values, formats, or analytical meaning. A table that exceeds supported slide constraints fails with a specific error or uses an explicit caller-selected density limit. Automated tests verify representative numeric, textual, aligned, captioned, and noted tables. | LaTeX table rendering and upstream creation of table data or semantics are outside this story. | Build on the shared table model and PowerPoint renderer. Inspect the chosen presentation library before specifying exact layout mechanisms. | FR-023, FR-025, FR-026 | WR-001, WR-004 | Story | New | wr-005-render-publication-tables-in-powerpoint | 364 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-006 | Render LaTeX reports and figures | Render the shared report model into valid LaTeX with document-native structure, semantic figures, and stable cross-references. | LaTeX output includes title matter, numbered sections, narrative paragraphs, methodology or appendices, figures, tables, and generated cross-references where applicable. Finding titles, subtitles, sources, captions, labels, numbering, and cross-reference metadata are outside chart images. Chart-content images retain axes, ticks, legends, series labels, data labels, reference-line labels, and analytical annotations. Shared finding semantics map to document-appropriate figure structures without reproducing PowerPoint layout literally. Stable figure labels allow narrative references independent of image contents. LaTeX output can be generated independently or with another renderer. | PowerPoint layout parity, chart construction, and analytical computation are outside this story. | Treat deterministic source generation as required. Whether local PDF compilation is bundled remains a release decision and must not prevent generation of valid source plus assets. | FR-003, FR-005, FR-007, FR-010, FR-039, FR-040, FR-041, FR-042 | WR-003 | Story | New | wr-006-render-latex-reports-and-figures | 365 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-007 | Render publication tables in LaTeX | Render shared publication tables as document-appropriate LaTeX tables with captions, notes, alignment, and scalable row handling. | LaTeX tables preserve the shared table's rows, values, display labels, formats, alignment, captions, and notes. Repeated headers, page breaks, and appendix-scale row counts are supported where the selected LaTeX package permits them. Renderer hints control placement or density without changing underlying data or analytical meaning. Unsupported width or pagination combinations fail with a specific error rather than silently dropping content. Automated tests verify representative concise, wide, and multi-page tables. | PowerPoint table rendering and upstream computation of table values are outside this story. | Choose LaTeX table packages after repository inspection and validate generated source with deterministic fixtures or compilation where the test environment supports it. | FR-024, FR-025, FR-026 | WR-001, WR-006 | Story | New | wr-007-render-publication-tables-in-latex | 366 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-008 | Resolve recurring report runs | Create isolated report instances from stable definitions, explicit run parameters, computed context, comparisons, and precomputed inclusion flags. | A stable report definition accepts reporting period, comparison period, benchmark, target, and other explicit run parameters without source modification. Each invocation creates an isolated report instance separate from the stable definition. Current, comparison, benchmark, target, and derived-change values supplied by analytics code are represented with first-class comparison semantics. Conditional findings use named precomputed flags or predicates from run context rather than Jinja business logic. The same programmatic generation path supports one-off and recurring reports with explicit parameters. Invalid or incomplete parameters fail before rendering with field-specific errors. | Scheduling, metric calculation, comparison calculation, and business-condition evaluation are outside this story. | Keep run resolution deterministic and stateless. Use fixtures for multiple periods to prove the authored definition is unchanged between runs. | FR-015, FR-016, FR-017, FR-018, FR-021 | WR-001, WR-002 | Story | New | wr-008-resolve-recurring-report-runs | 367 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-009 | Persist deterministic run outputs and manifests | Write isolated, caller-directed report outputs and diagnostic manifests without corrupting successful artifacts. | Each recurring run records report identity, run parameters, definition version when available, referenced input artifacts, outputs, and generation status. Callers can select immutable output directories organized by report and reporting period. Identical inputs and templates produce identical structure, ordering, text, and selected artifact placement. Failure of one renderer leaves successful outputs from other renderers intact and records each target's status. Existing artifacts are not overwritten unless replacement is explicitly requested. Partial failures preserve enough manifest metadata to identify the failing target and input. | Scheduling, artifact synchronization, and a general artifact registry are outside this story. | Use atomic per-target writes where the chosen filesystem APIs permit them. Test successful dual-renderer runs, partial failure, collision refusal, and explicit replacement. | FR-019, FR-020, QR-001, QR-002, QR-006 | WR-004, WR-006, WR-008 | Story | New | wr-009-persist-deterministic-run-outputs-and-manifests | 368 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-010 | Publish a protected LaTeX source workspace | Emit a self-contained LaTeX source tree and safely publish generated content to a mutable workspace alongside human-maintained extensions. | The renderer emits generated .tex files and referenced assets as a self-contained source tree suitable for external compilation. A caller can publish generated source to a mutable workspace independently from immutable archived runs. Generated and human-maintained paths have an explicit ownership boundary. Regeneration does not silently overwrite human-maintained extensions or appendices. External synchronization can consume the workspace without Wood Reports implementing synchronization. Tests prove generated updates preserve human-maintained extension files. | Overleaf synchronization, two-way file synchronization, and implicit replacement of generated sections by extensions are outside this story. | Use a documented generated/ and extensions/ boundary or an equivalently explicit layout selected during repository design. Keep the synchronization interface filesystem-based. | FR-027, FR-028, FR-029, FR-030, FR-037 | WR-006, WR-008, WR-009 | Story | New | wr-010-publish-a-protected-latex-source-workspace | 369 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-011 | Expose the report generation API | Expose a typed Python API that validates, compiles, and invokes selected renderers while isolating optional renderer dependencies. | Python consumers can invoke validation, compilation, and one or both renderers through a documented programmatic API. One-off and recurring calls use the same API with explicit run parameters where applicable. PowerPoint-only installation and execution do not require LaTeX-specific dependencies, and LaTeX-only installation and execution do not require PowerPoint-specific dependencies. Public API interfaces are type annotated and covered by automated tests. Renderer failures are returned with target-specific status while preserving successful outputs. | A CLI, scheduler integration, orchestration service, and general plugin framework are outside this story. | Inspect packaging conventions before defining extras or entry points. Test each optional dependency configuration and the combined configuration. | FR-009, FR-010, FR-021, QR-002, QR-004, QR-005 | WR-002, WR-004, WR-006, WR-008, WR-009 | Story | New | wr-011-expose-the-report-generation-api | 370 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.
Wood Reports | Wood Reports V0.1 Foundation | V0.1 Foundation | Wood Reports MVP | Wood Reports MVP | WR-012 | Document the production analytics integration | Document and demonstrate how an analytics repository supplies metrics, charts, tables, declarative reports, and orchestration to Wood Reports. | Documentation defines recommended landing zones for notebooks, SQL, reusable metrics, chart builders and registries, publication-table builders, declarative reports, and report-build orchestration. The recommended shape marks layers as optional where they are not needed. An example demonstrates logical chart resolution, publication-table construction, declarative authoring, and generation of both output formats. The example keeps analytical computation in the consuming project and publication mechanics in Wood Reports. Documented commands and paths are verified against the initialized repositories before publication. | Creating a mandatory repository framework or moving exploratory notebook work into Wood Reports is outside this story. | Use synthetic-website-analytics and wood-charts as the first integration example after inspecting their live repository structures. Keep main.py, if present, as a thin entrypoint. | FR-038 | WR-003, WR-005, WR-007, WR-010, WR-011 | Story | New | wr-012-document-the-production-analytics-integration | 371 | Imported from Google Drive Wood Reports Story Backlog; source status was Draft.

## Sync Metadata
Field | Value
Configured Root Work Package ID
Verified Root Work Package ID | 358
Root Work Package Subject | Wood Reports V0.1 Foundation
Root Work Package Type | Initiative
Root Work Package OpenProject URL | https://projects.woodhost.cloud/work_packages/358
Ancestry Validation Status
Exported At
Story Count
Status Summary